## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Murugu Zachary 23509124
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | to play the game
|  | 3 | control the direction which the snake moves
|  | 4 | get notified when I score a point/win
|  | 5 | to be notified when I loose or "die"
|  | 6 | to be notified when the game is over

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Your name and student ID
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form
3.1.3 |  |  | GUI for the snake
3.1.4 |  |  | GuI for the prey
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
Prey position logic
winning logic
Crushing/losing logic
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%